## Budget Guidance
Budget Guidance
Cost Estimate: The cost estimate matches the proposed level of effort from the SOW and work schedule. Cost estimates are to be listed under the approved cost item categories; Materials, Labor, and/or Fees. Source materials used to support the cost estimate are referenced and include sufficient detail so FDEM can determine whether costs are reasonable based on proposed activities and level of effort.
Ø Cost Share: The cost estimate identified in the cost categories include the Local Match / Non-Federal Share
Ø Pre-award Costs: To be eligible for HMA funding and/or as a cost-share, pre-award costs must be included as separate line items in the cost estimate. Must include a completed Pre-Award Cost Form with application. (Separate line item, identified as either Phase I pre-award, Phase II/Mon-Phase Pre-Award - under the Fees category)
Ø Ineligible Format: Lump-sum cost estimates in this workbook are not eligible and will be NOT be accepted for application submittal.
Ø Contingency Cost: Is an allowance included in the total cost estimate to cover situations that cannot be fully defined at the time the cost estimate is prepared, but that will likely result in additional eligible costs (HMA Guidance Part VI, D.3.4). A contingency cost should be included as a separate line item in the budget section of a project application. As with other line items in the budget, the applicant should justify the contingency estimate based on the nature of the proposed project. (Calculated at a maximum of 5% of project costs.
Under the HMA programs, the total cost to implement approved mitigation activities is generally funded by a combination of Federal and non-Federal sources. Both the Federal and the non-Federal cost shares must be for eligible costs used in direct support of the approved activities under this guidance and the award. Contributions of cash, third-party in-kind services, other non-Federal sources, or any combination thereof, may be accepted as part of the non-Federal cost share (Must submit the documentation to support).
FEMA administers cost-sharing requirements consistent with 2 CFR Sections 200.29, 200.306, and 200.434. To meet cost-sharing requirements, the non-Federal contributions must be verifiable from the subrecipient’s records, reasonable, allowable, allocable, and necessary under the grant program and must comply with all Federal requirements and regulations.
In general, HMGP Federal funds may be used to pay up to 75 percent of the eligible activity costs. The remaining 25 percent of eligible activity costs are derived from the identified non-Federal sources.
For the cost sections relating to Materials, Labor, and Fees, it is important to note,
Ø Lump sums without supporting documentation showing a breakdown of those costs are not acceptable. For those items that will not fit in the spaces provided, attach the appropriate documentation to your application.
Ø Identify your match sources in Funding Summary - Section I
Ø Sub-Total cells will auto sum the costs in their respective columns.
Ø Do not factor Sub-Recipient Management Costs (SRMC) into Section IV - parts A-C. If requesting SRMC enter information into "SR Mgmt. Costs" tab - Part G.
Ø Contingency Costs need to be justified and reported as a separate line item in part E of this section. From left to right in that part, enter the desired percentage (maximum 5% of Material/Labor), the amount the percentage is to be applied to, and the resulting amount. PLEASE NOTE- These cells will not auto-calculate across the row, but the final cell will be calculated into the Final Project Cost below it. Take care that everything is calculated correctly. (Adjust down to whole dollar (cents) in cell G106, and/or G107).
Ø Pre-Award Costs: costs must be identified as a separate line item, AND a completed HMGP Pre-Award Cost Request Form MUST be submitted with this application, detailing the items/cost and requested start date.
Under Labor (part B) mark all In-kind (donated) services with (**); In-house (employee) services with (***), per each line item, as applicable.
Ø All funding sources (In-kind, In-house, Global Match, and Other Agencies) must be identified (below) AND identified on the Funding Sources - Section IV - I.
Sub-Recipient Management Costs (SRMC)
For SRMC, in compliance with Disaster Relief and Recovery Act of 2018 (DRRA) and the subsequent FEMA Interim Policy #104-11-1, the Florida Division of Emergency Management has included a section for applicants to request, or refuse, project management funds that are available to them. Under this new policy, HMGP projects awarded under disasters declared on or after August 1, 2017, are eligible for project management costs up to 5 percent of their total project costs.
Applicants choosing to apply for this funding must detail the specific administrative costs in Part G of this section. These costs must be eligible administrative costs, conforming to the requirements set in 2 CFR Part 200 Subpart E. Applicants must ensure that their administrative costs are reasonable, allowable, allocable, and necessary for the performance of the federal award.
The State will allot these management costs on a project-by-project basis per the amount requested by the sub-recipient, up to 5 percent of the total project cost. A sub-recipient may request less than this, but no higher. These management costs will be considered a separate pool of funding and WILL NOT affect a project’s benefit-cost analysis.
Management costs will be reimbursed per reimbursement request, and no more than 5 percent of any given reimbursement request amount. All management costs reimbursements will be contingent upon adequate documentation from the sub-recipient.
Management costs will be reimbursed at 100 percent of the amount of management costs requested, so far as they are adequately documented and are no more than 5 percent of the request. Any unused management costs at closeout following the final payment will be de-obligated. If the final total project cost results in an under-run, management costs will be reduced accordingly.
Applicants must make the determination to request or refuse management costs at the time of formal application submittal. The State will accept the initial determination from the applicant. There will be no recourse from the State for applicants wishing to change their initial determination after the application has been formally submitted.
PRE-AWARD COSTS
Pre-award costs directly related to developing the application or subapplication may be funded through HMA as funds are available. Such costs may have been incurred, for example, to develop a BCA, to gather EHP data, for preparing design specifications, or for workshops or meetings related to development and submission of HMA applications and subapplications. Costs associated with implementation of the activity but incurred prior to Federal award or final approval are not eligible (projects initiated or completed prior to Federal award or full approval of the project are not eligible). Pre-award management costs count towards the 5 percent limit for subrecipient management costs. To be eligible for HMA funding, pre-award costs must be identified as separate line items in the cost estimate of the subapplication. Applicants and subapplicant's may identify such pre-award costs as their non-Federal cost share. Applicants and subapplicant's who are not awarded grants or subawards will not receive reimbursement for the corresponding pre-award costs.
SUB-RECIPIENT MANAGEMENT COSTS (SRMC) PRE-AWARD COSTS
Pre-award Sub-Recipient Management Costs (SRMC) directly related to developing the SRMC application or subapplication only. may be funded through HMA as funds are available, and must be requested at the time of application submittal. Pre-award management costs count towards the 5 percent limit for subrecipient management costs. To be eligible for HMA funding, pre-award costs must be identified as separate line items in the SRMC estimate of the subapplication. Applicants and subapplicant's who are not awarded grants or subawards will not receive reimbursement for the corresponding pre-award costs.
2 CFR 200 compliance
2 CFR 200.209- Pre-Award Costs: For requirements on costs incurred by the applicant prior to the start date of the period of performance of the Federal award, see §200.458 Pre-award costs
2 CFR 200.458- Pre-Award Costs: Pre-award costs are those incurred prior to the effective date of the Federal award directly pursuant to the negotiation and in anticipation of the Federal award where such costs are necessary for efficient and timely performance of the scope of work. Such costs are allowable only to the extent that they would have been allowable if incurred after the date of the Federal award and only with the written approval of the Federal awarding agency.
2015 HMA Guidance: Costs incurred after the HMA application period has opened, but prior to the date of the Federal award or final approval, are identified as pre-award costs. For HMGP, the opening of the application period is the date when HMGP is authorized, which is generally the date of the Presidential major disaster declaration.

## Budget
Section IV. Budget/Costs | [6 empty] | 06/15/21 - DO NOT ADD LINES/ROWS TO THIS DOCUMENT - DO NOT HIDE ANY COLUMNS CURRENTLY SHOWING
[5 empty] | ID# 4673-DR-FL |  | ID # = Disaster number-(application#), then replaced with FEMA project #-(app#)
COMPL
| This section, provide details of all the estimated costs of the project. As this information is used for the Benefit-Cost Analysis, reasonable cost estimates are essential. Pre-Award Costs, Project Management, and any Contingency (maximum 5%) need to be reported as separate line items. All cost estimates rounded to the nearest dollar. | [5 empty] | FDEM-PM SECTION ONLY Use To Complete Attachment A |  |  |  |  | Autocalculated from cell E105 or Type in the actual percentage amount - go out as many decimal points to match the Federal amount | PM totals | PM Federal | PM Local | COMMENTS
A. | Materials: Any Material utilized to complete project (include acquistion of property) | [5 empty] | ADJ |  | 75% | 25% | ADJ
| Item | Unit | Qty | Cost / Unit | Cost |  | Fed | Totals | Federal Share | Non-Federal
| Erosion Control | LS | 1 | 40500 | 40500
| Excavation | CY | 150 | 13.68 | 2052
| Embankment | CY | 750 | 25.26 | 18945
| Optional Base, Base Group 6 | CY | 930 | 28.03 | 26067.9
| Asphalt Concrete Friction Course | CY | 430 | 147.82 | 63562.6
| Superpave Asphaltic Concrete | CY | 430 | 109.5 | 47085
| Inlets, Ditch Bottom, Type C | EA | 10 | 5359.3 | 53593 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN (right mouse click row(s)-choose hide)
| Baffle Boxes | EA | 2 | 50000 | 100000 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
| Pipe Culverts 18' | LF | 1200 | 130.51 | 156612 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
| Pipe Culverts 24' | LF | 500 | 158.7 | 79350 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
| Restorations Per Lot | EA | 45 | 1500 | 67500 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
| Utlity Adjustments per lot | EA | 45 | 1000 | 45000 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
| Backflow | EA | 2 | 25000 | 50000 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
| Performance Turf | SY | 5430 | 3.53 | 19167.9 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
| Driveway Restorations per lot | EA | 45 | 3000 | 135000 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
|  |  |  | Sub-Total | 904435.4 |  | 0 | 904435.4 | 678326.55 | 226108.85
B. | Labor: Include equipment costs. Please indicate all "soft", In-house(***), or In-kind matches-donated (**).
| Description of Task |  | Qty | Rate | Cost
| Phase I - Mobilization |  | 1 | 67600 | 67600 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
| Phase I - Maintenance of Traffic |  | 1 | 67600 | 67600 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
| Phase I - |  |  |  | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
| Phase I - |  |  |  | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
| Phase I ONLY- Sub-total |  |  | 135200 |  |  | 0 | 135200 | 101400 | 33800 |  | If no Phase I Labor costs - LEAVE BLANK and ONLY HIDE lines 64-67 - DO NOT HIDE THIS LINE
0
0
0
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN ONLY
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
| Non-Phased or Phase II - Sub-total |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  |  |  | Sub-Total | 135200 |  | 0 | 135200 | 101400 | 33800
C. | Fees Paid Include any other costs associated with the project.
| Description of Task |  | Qty | Rate | Cost |  |  |  | 75% |  |  | If Phase I Federal share is different from Phase II - adjust in colum K - If not do NOT change
| Phase I - Pre-Award with start date of _/_/_ |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | Pre-Award form Must be included - (cost incurred after declaration & before grant awarded)-DO NOT OVERWRITE LINE - Only Add date
| Phase I - Professional Engineering Services |  |  |  | 0
| Phase I - General Conditions and Bonding |  | 1 | 128848 | 128848
| Phase I - Survey, Layout and Field Staking |  | 1 | 77309 | 77309
| Phase I - Final Record Drawings and Final Submitals |  | 1 | 51539 | 51539
| Phase I - Contingency (5%) |  | 1 | 57517.94 | 57517.94
| Phase I - |  |  |  | 0 |  | 0 | 315213.94 | 236410.455 | 78803.485 |  | Phase I Fees (not including Pre-Award) -
| Phase I ONLY- Sub-total |  |  | 315213.94 |  |  | 0 | 315213.94 | 236410.455 | 78803.485 |  | If no Phase I activites - LEAVE BLANK and HIDE lines 100-106 ONLY
| Non-Phased - Pre-Award with start date of _/_/_ |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | Non-Phased Pre-Award (only) Form Must be included - (cost incurred after declaration & before grant awarded)-DO NOT OVERWRITE LINE - Only Add date
0
0
0
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN - ONLY
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
[5 empty] | 0 | [6 empty] | HIDE any unused/blank lines FROM HERE DOWN
| Non-Phased or Phase II - Sub-total |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  |  |  | Sub-Total | 315213.94 |  | 0 | 315213.94 | 236410.455 | 78803.485
D. |  |  |  | Sub-Total Estimated Project Cost | 1354849.34 |  | 0 | 1354849.34 | 1016137.005 | 338712.335
E. | Contingency Costs (max 5%) Phase I | 0% |  | 450413.94 | 0 | 0 | 0 | 0 | 0 | 0 |  | Round Contingency down to the whole dollar (ADJ in cell G84)
| Contingency Costs (max 5%) Non-Phased or Phase II | 0% |  | 904435.4 | 0 | 0 | 0 | 0 | 0 | 0 |  | Round Contingency down to the whole dollar (ADJ in cell G85)
| Total Contingency Costs (maximum 5%) |  |  | 1354849.34 | 0 |  | 0 | 0 | 0 | 0
F. |  |  |  | Final Estimated Project Costs | 1354849.34 |  | 0 | 1354849.34 | 1016137.005 | 338712.335
|  |  | Phase I Subtotal | 450413.94 |  |  | 0 | 450413.94 | 337810.455 | 112603.485
|  |  | Non-Phased or Phase II Subtotal | 904435.4 |  |  | 0 | 904435.4 | 678326.55 | 226108.85
| Note: Backup source documentation is required to support costs |  |  | 1354849.34 |  |  | 0 | 1354849.34 | 1016137.005 | 338712.335
[9 empty] | 75% | 25%
| Comments: |  |  | Federal | Project Cost | [6 empty] | the Federal share is input from the Funding summary or Funding Summary (find %) - do not put a calculation Hin cell E105) - other cells are already calculated from this cell - HMS
| Federal Share Percentage Requesting (per LMS) |  |  | 75%
| Sub-Recipient Federal Amount Endorsed by LMS |  |  | 0 |  |  |  | DIFFERENCE | -1016137.005 | IF NEGATIVE-REVISE %
FEMA Approval 00/00/00

## SR Mgmt Costs
ID# 4673-DR-FL
G. | Sub-Recipient Management Costs
Based on the amount of federal share being requested in Part F, your project is eligible for up to an additional 5% of the project costs for Sub-Recipient Management Costs. Please indicate below whether or not you would like to request these funds and follow the directions for your selected choice. In addition a Request Form is Required.
Total Estimated Project Costs (Budget F.) | [6 empty] | 1354849.34 |  | Maximum SRMC Allowed
[7 empty] | 5% |  | Phase I | Non-Phased or Phase II
Total Estimated SR Management Costs Available (5% of Total Project Costs) | [6 empty] | 67742.467 | SRMC Estimated Available | 22520.697 | 45221.77
Note: This number will be generated automatically after Budget line items are completed
| YES | I would like to requests these funds (please fill out the itemized table below, then continue to Part I)*
| NO | I do not wish to request these funds. (continue to Part I)*
| Descriptions of SRMC |  |  |  | Qty | Rate | Cost |  |  | Maximum SRMC | 22520.697
| Phase I SRMC (per SRMC Request Form) | [6 empty] | Year 1 | Year 2 | Year 3 | TOTAL
1 | Ph I - SRMC Application development (Pre-Award)
2 | Ph I - Pre-Award - Personnel (Sub-Recipient In-House) | [5 empty] | 0 |  |  |  | 0
3 | Ph I - Pre-Award - Contractual Services | [5 empty] | 0 |  |  |  | 0
4 | Ph I - Personnel (Sub-Recipient In-House) | [5 empty] | 0 |  |  |  | 0
5 | Ph I - Contractual Services | [5 empty] | 0 |  |  |  | 0
6 | Ph I - Indirect Costs | [5 empty] | 0 |  |  |  | 0
7 | [6 empty] | 0 |  |  |  | 0
8 | [6 empty] | 0 |  |  |  | 0
9 | [6 empty] | 0 |  |  |  | 0
10 | [6 empty] | 0 |  |  |  | 0
11 | [6 empty] | 0 |  |  |  | 0
12 | [6 empty] | 0 |  |  |  | 0
| Sub-Total of Phase I SRMC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 22520.697 | If Negative amount - Revise requested amount
| Non-Phased or Phase II SRMC (per SRMC Request Form) | [6 empty] | Year 1 | Year 2 | Year 3 | TOTAL
1 | SRMC Application development (Non-Phased Pre-Award)
2 | Pre-Award - Personnel (Sub-Recipient In-House) | [5 empty] | 0 |  |  |  | 0
3 | Pre-Award - Contractual Services | [5 empty] | 0 |  |  |  | 0
4 | Personnel (Sub-Recipient In-House) | [5 empty] | 0 |  |  |  | 0
5 | Contractual Services | [5 empty] | 0 |  |  |  | 0
6 | Indirect Costs | [5 empty] | 0 |  |  |  | 0
7 | [6 empty] | 0 |  |  |  | 0
8 | [6 empty] | 0 |  |  |  | 0
9 | [6 empty] | 0 |  |  |  | 0
10 | [6 empty] | 0 |  |  |  | 0
11 | [6 empty] | 0 |  |  |  | 0
| Sub-Total of Non-Phased or Phase II SRMC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 45221.77 | If Negative amount - Revise requested amount
H. |  |  | Total Estimated SRMC Requested |  |  |  | 0 |  |  |  | 0
[6 empty] | Difference | 67742.467 | If negative - you have requested too much - Revise Requested costs
Note: By selecting either “yes” or “no” the Sub-Applicant / Sub-Recipient is acknowledging that they understand what is being offered to them as it is described in this application.
All costs must be reasonable, allowable, allocable, and necessary as required by 2 CFR Part 200 Subpart E, applicable program regulations, and HMA Guidance (2015)
|  |  |  | Maximum SRMC: |  |  | 67742.467
HMGP Management Costs (Interim) Policy # 104-11-1 FAQ, March 23, 2020
Typically, a non-construction budget for management costs will include but the following cost categories: personnel, fringe benefits, travel, equipment, supplies, contractual, and indirect costs. A brief narrative may be required to identify what the funds will be used for. These are required fields in the Application.
Administrative costs are expenses incurred by a recipient or a subrecipient in managing and administering the federal award to ensure that federal, state, or tribal requirements are met including:
• solicitation, development, review, and processing of the actual SRMC subapplication
NOTE: only cost allowed for Pre-Award SRMC - completing the SRMC Request form
• delivery of technical assistance;
• quarterly progress and fiscal reporting;
• project monitoring;
• technical monitoring;
• compliance activities associated with federal procurement requirements;
• documentation of quality of work verification for quarterly reports and closeout;
• payment of claims;
• closeout review and liquidation; and
• records retention.

## Funding Summary
I. | Funding Sources (round figures to the nearest dollar) | [5 empty] | ID# 4673-DR-FL
| The maximum FEMA share for HMGP/HMA projects is 75%. The other 25% can be made up of State and Local funds as well as in-kind services. Moreover, the FMA program requires that the maximum in-kind match be no more than 12.5 % of the total projects costs. HMGP/FMA funds may be packaged with other Federal Funds, but other Federal funds (except for Federal funds which lose their Federal identity at the State level - such as CDBG, ARS, HOME) may not be used for the State or Local match. | [7 empty] | Awarded Amount | Increase / Decrease
ADJ
1 | Estimated FEMA Share |  |  | 1016137.005 | 75% | % of Total | (maximum of 75%) | 0 | 0 | 1016137.005
2 | Non-Federal Share
3 |  | Estimated Local Share |  | 338712.335 | 25% | % of Total | (Cash) | 0 | 0 | 338712.335
4 |  |  |  | 0 | 0% | % of Total | (In-Kind**) | 0 | 0 | 0
5 |  |  |  | 0 | 0% | % of Total | (In-House***) | 0 | 0 | 0
6 |  |  |  | 0 | 0% | % of Total | (Global Match****) | 0 | 0 | 0
7 | Other Agency Share |  |  | 0 | 0% | % of Total |  | 0 | 0 | 0
| (Identify Other Non-Federal Agency and availability date) | [5 empty] | Amounts
0
0
8 | Total Funding |  |  | 1354849.34 | 100% | Total % | (should equal 100%) | 0 | 0 | 1354849.34
** Identify proposed eligible activities directly related to project to be considered for In-Kind (donated) services
*** Identify proposed eligible activities directly related to project to be considered for In-House services
**** Separate project applications must be submitted for each project (Global) Match project.
Global Match Project # and Title:
9 | Total Estimated SR Management Costs |  | Requested | 0 |  |  |  |  | 0 | 0
|  |  | Available | 67742.467 | 5% | of Total | (Max Allowed)
|  |  |  | 67742.467 | If negative amount - revise SR Mgmt Costs |  |  |  | 0 | 1354849.34
J. | Project Milestones/Schedule of Work
List the major milestones in this project by providing an estimate time-line for the critical activities not to exceed a period of 36-month of performance. (e.g. Designing, Engineering, Permitting, etc.)
If 24 months change column K to the following
|  | Milestone |  |  | Number of Months to Complete |  |  |  | Number of Months to Complete
|  | State and Local Contracting |  |  |  | 3 | Months |  |  | 3 | Months
|  | Construction Plan /Techncial Specifications |  |  |  | 3 | Months |  |  | 2 | Months
|  | Bidding / Local Procurement |  |  |  | 3 | Months |  |  | 2 | Months
|  | Permitting |  |  |  | 3 | Months |  |  | 2 | Months
|  | Construction / Installation |  |  |  | 15 | Months |  |  | 9 | Months
|  | Local Inspections / Compliance |  |  |  | 3 | Months |  |  | 2 | Months
|  | State Final Inspections / Compliance |  |  |  | 3 | Months |  |  | 2 | Months
|  | Closeout Compliance |  |  |  | 3 | Months |  |  | 2 | Months
[5 empty] | 36 |  |  |  | 24
OR
|  | Milestone |  |  | Number of Months to Complete
|  | Phase I - State and Local Contracting |  |  |  | 2 | Months
|  | Phase I - Bidding / Local Procurement |  |  |  | 2 | Months
|  | Phase I - Design Specifications |  |  |  | 4 | Months
|  | Phase I - Permitting |  |  |  | 2 | Months
|  | Phase I - Deliverables submittal to FDEM |  |  |  | 2 | Months
12
|  | Phase II - State and Local Contracting |  |  |  | 3 | Months
|  | Phase II - Construction Plan /Techncial Specifications |  |  |  | 1 | Month
|  | Phase II - Bidding / Local Procurement |  |  |  | 2 | Months
|  | Phase II - Construction / Installation |  |  |  | 11 | Months
|  | Phase II - Local Inspections / Compliance |  |  |  | 2 | Months
|  | Phase II - State Final Inspections / Compliance |  |  |  | 3 | Months
|  | Phase II - Closeout Compliance |  |  |  | 2 | Months
24
[6 empty] | 36 | Months

## Funding Summary (find %)
I. | Funding Sources (round figures to the nearest dollar) | [5 empty] | ID# 4673-DR-FL
| The maximum FEMA share for HMGP/HMA projects is 75%. The other 25% can be made up of State and Local funds as well as in-kind services. Moreover, the FMA program requires that the maximum in-kind match be no more than 12.5 % of the total projects costs. HMGP/FMA funds may be packaged with other Federal Funds, but other Federal funds (except for Federal funds which lose their Federal identity at the State level - such as CDBG, ARS, HOME) may not be used for the State or Local match. | [7 empty] | Column H - Add the Actual Federal Share (LMS), Local Share, Other Agency
|  |  |  | $ Endorsed | Do NOT Overwrite |  |  | ADJ | Column H - Add the Actual Federal Share (LMS), Local Share, Other Agency
1 | Estimated FEMA Share |  |  | 0 | 0% | % of Total | (maximum of 75%) | 0 | Federal Share allocated by the LMS Endorsement Letter
[9 empty] | Non-Federal Share |  | $ needs | difference
2 | Non-Federal Share | [7 empty] | 0 | 0% | 1354849.34 | 1354849.34
3 |  | Estimated Local Share |  | 0 | 0% | % of Total | (Cash) | 0 | 0% | PM type in the actual Federal share percentage (from cell J6)and input on Budget tab cell E117
100%
4 |  |  |  | 0 | 0% | % of Total | (In-Kind**) | 0
5 |  |  |  | 0 | 0% | % of Total | (In-House***) | 0
6 |  |  |  | 0 | 0% | % of Total | (Global Match****) | 0
0
7 | Other Agency Share |  |  | 0 | 0% | % of Total |  | 0
(Identify Other Agency and availability date)
8 | Total Funding |  |  | 1354849.34 | 100% | Total % | (should equal 100%) | 0
** Identify proposed eligible activities directly related to project to be considered for In-Kind services. (note on page 4 Section B)
*** Identify proposed eligible activities directly related to project to be considered for In-Kind services. (note on page 4 Section B)
**** Separate project applications must be submitted for each project (Global) Match project.
Global Match Project # and title:
9 | Total Estimated SR Management Costs |  | Requested | 0
|  |  | Available | 67742.467 | 5% | of Total | (Max Allowed)
J. | Project Milestones/Schedule of Work
List the major milestones in this project by providing an estimate time-line for the critical activities not to exceed a period of 36 months of performance. (e.g. Designing, Engineering, Permitting, etc.)
|  | Milestone |  |  | Number of Days to Complete
|  | State and Local Contracting |  |  |  | 3 | Months
|  | Construction Plan /Techncial Specifications |  |  |  | 3 | Months
|  | Bidding / Local Procurement |  |  |  | 4 | Months
|  | Permitting |  |  |  | 3 | Months
|  | Construction / Installation |  |  |  | 3 | Months
|  | Local Inspections / Compliance |  |  |  | 14 | Months
|  | State Final Inspections / Compliance |  |  |  | 3 | Months
|  | Closeout Compliance |  |  |  | 3 | Months
36
OR
|  | Milestone |  |  | Number of Days to Complete
|  | Phase I - State and Local Contracting |  |  |  | 2 | Months
|  | Phase I - Bidding / Local Procurement |  |  |  | 2 | Months
|  | Phase I - Design Specifications |  |  |  | 4 | Months
|  | Phase I - Permitting |  |  |  | 2 | Months
|  | Phase I - Deliverables submittal to FDEM |  |  |  | 2 | Months
12
|  | Phase II - State and Local Contracting |  |  |  | 3 | Months
|  | Phase II - Construction Plan /Techncial Specifications |  |  |  | 1 | Month
|  | Phase II - Bidding / Local Procurement |  |  |  | 2 | Months
|  | Phase II - Construction / Installation |  |  |  | 11 | Months
|  | Phase II - Local Inspections / Compliance |  |  |  | 2 | Months
|  | Phase II - State Final Inspections / Compliance |  |  |  | 3 | Months
|  | Phase II - Closeout Compliance |  |  |  | 2 | Months
24
[6 empty] | 36 | Months
[6 empty] | 64 | Months

## Code Plus
Project: _____(Applicant, Site), Code Plus
Disaster #:
Item Description | Unit | Qty | Cost for Current Code/Standard of ___-MPH | Cost for Code Plus to ___-MPH | Cost to Harden/Code Plus Code plus less Standard (E-D) | Input current Wind speed for site (D) Input Wind speed for Code Plus (E)
Phase I Costs | [5 empty] | Round off (don't include cents)
Fees: Pre-Award-Application Development | 1 | LS | 0 | 0 | 0
Fees: Pre-Award-Design | 1 | LS | 0 | 0 | 0
Fees: Architectural/Engineering Fees | 1 | LS | 0 | 0 | 0
Fees: Permitting | 1 | LS | 0 | 0 | 0
Fees: Safe Room-Engineering (if applicable) | 1 | LS | 0 | 0 | 0
Fees: | 1 | LS | 0 | 0 | 0
Fees: | 1 | LS | 0 | 0 | 0
Sub-Total Phase I |  |  | 0 | 0 | 0 | Rounding (H13)
Phase II Construction Costs | [5 empty] | provide list of specifics items included
Materials: Hurricane Straps (roof) | 1 | SF | 0 | 0 | 0
Materials: Windows/Impact Glass | 1 | EA | 0 | 0 | 0
Materials: High Impact Shutters | 1 | EA | 0 | 0 | 0
Materials: Doors & Windows | 1 | EA | 0 | 0 | 0
Materials: Floor Straps - trusses | 1 | SF | 0 | 0 | 0
Materials: Concrete | 1 | SF | 0 | 0 | 0
Materials: Metals | 1 | SF | 0 | 0 | 0
Materials: Carpentry | 1 | SF | 0 | 0 | 0
Materials: Thermal Moisture Protection | 1 | SF | 0 | 0 | 0
Materials: Equipment | 1 | EA | 0 | 0 | 0
Materials: HVAC | 1 | LS | 0 | 0 | 0
Materials: Finishes | 1 | LS | 0 | 0 | 0
Materials: Electrical | 1 | LS | 0 | 0 | 0
Materials: Safe Room-Personnel | 1 | LS | 0 | 0 | 0
Materials: Generator __kW | 1 | EA | 0 | 0 | 0
Materials: Generator-Concrete Pad | 1 | SF | 0 | 0 | 0
Materials: Roof | 1 | SF | 0 | 0 | 0
Materials: Walls | 1 | SF | 0 | 0 | 0
Materials: Foundation | 1 | SF | 0 | 0 | 0
Materials: __ | 1 | SF | 0 | 0 | 0
Materials: __ | 1 | SF | 0 | 0 | 0
Materials: __ | 1 | LS | 0 | 0 | 0
Materials Total |  |  | 0 | 0 | 0 | Rounding (H38)
Labor: Installation | 1 | LS | 0 | 0 | 0
Labor: | 1 | LS | 0 | 0 | 0
Labor: | 1 | LS | 0 | 0 | 0
Labor Total |  |  | 0 | 0 | 0 | Rounding (H42)
Fees: Construction Inspections | 1 | LS | 0 | 0 | 0
Fees: Certified As-built | 1 | LS | 0 | 0 | 0
Fees: ___ | 1 | LS | 0 | 0 | 0
Fees: ___ | 1 | LS | 0 | 0 | 0
Fees: ___ | 1 | LS | 0 | 0 | 0
Fees Total |  |  | 0 | 0 | 0
Phase II Sub-Total |  |  | 0 | 0 | 0
Phase I-Contingency (Max. 5% of Ph I cost) |  |  | 0 | 0 | 0 | round down to nearest $ in cell H51
Phase II-Contingency (Max. 5% of Ph I cost) |  |  | 0 | 0 | 0 | round down to nearest $ in cell H52
Total Project Cost |  |  | 0 | 0 | 0
Construction Sitework (with no Code plus Difference)
Clearing and Grubbing | 1 | LS | 0 | 0
Earthwork/Site Grading | 1 | LS | 0 | 0
Base | 1 | LS | 0 | 0
Asphalt | 1 | LS | 0 | 0
Stabilized Sub-grade | 1 | LS | 0 | 0
Site Utilities | 1 | LS | 0 | 0
Stormwater Management Facilities | 1 | LS | 0 | 0
Landscaping | 1 | LS | 0 | 0
| 1 | LS | 0 | 0
| 1 | LS | 0 | 0
| 1 | LS | 0 | 0
| 1 | LS | 0 | 0
| 1 | LS | 0 | 0
| 1 | LS | 0 | 0
| 1 | LS | 0 | 0
| 1 | LS | 0 | 0
| 1 | LS | 0 | 0
| 1 | LS | 0 | 0
| 1 | LS | 0 | 0
| 1 | LS | 0 | 0
Sitework Total |  |  | 0 | 0
Total |  |  | 0 | 0 | 0

## PH I - Summary
I. | Funding Sources (round figures to the nearest dollar) | [5 empty] | ID# 4673-DR-FL
Phase I
| The maximum FEMA share for HMGP/FMA projects is 75%. The other 25% can be made up of State and Local funds as well as in-kind services. Moreover, the FMA program requires that the maximum in-kind match be no more than 12.5 % of the total projects costs. HMGP/FMA funds may be packaged with other Federal Funds, but other Federal funds (except for Federal funds which lose their Federal identity at the State level - such as CDBG, ARS, HOME) may not be used for the State or Local match. | [7 empty] | Awarded Amount | Increase / Decrease
ADJ
1 | Estimated FEMA Share |  |  | 337810.455 | 75% | % of Total | (maximum of 75%) | 0 | 0 | 337810.455
2 | Non-Federal Share
3 |  | Estimated Local Share |  | 112603.485 | 25% | % of Total | (Cash) | 0 | 0 | 112603.485
4 |  |  |  | 0 | 0% | % of Total | (In-Kind*) | 0 | 0 | 0
5 |  |  |  | 0 | 0% | % of Total | (In-House***) | 0 | 0 | 0
6 |  |  |  | 0 | 0% | % of Total | (Global Match**) | 0 | 0 | 0
7 | Other Agency Share |  |  | 0 | 0% | % of Total |  | 0 | 0 | 0
(Identify Other Non-Federal Agency and availability date)
0
0
8 | Total Funding sources from above |  |  | 450413.94 | 100% | Total % | (should equal 100%) | 0 | 0 | 450413.94
** Identify proposed eligible activities directly related to project to be considered for In-Kind (donated) services
*** Identify proposed eligible activities directly related to project to be considered for In-House services
**** Separate project applications must be submitted for each project (Global) Match project.
Global Match Project # and title:
9 | Total Estimated SR Management Costs |  | Requested | 0 |  |  |  |  | 0 | 0
|  |  | Available | 22520.697 | 5% | of Total | (Max Allowed)
|  |  |  | 22520.697 | If negative - revise SR Mgmt Costs - tab |  |  |  | 0 | 450413.94
J. | Project Milestones/Schedule of Work
List the major milestones in this project by providing an estimate time-line for the critical activities not to exceed a period of 36-month of performance. (e.g. Designing, Engineering, Permitting, etc.)
|  | Milestone |  |  | Number of Days to Complete
|  | Phase I - State and Local Contracting |  |  |  | 2 | Months
|  | Phase I - Bidding / Local Procurement |  |  |  | 2 | Months
|  | Phase I - Design Specifications |  |  |  | 4 | Months
|  | Phase I - Permitting |  |  |  | 2 | Months
|  | Phase I - Deliverables submittal to FDEM |  |  |  | 2 | Months
12
|  | Phase II - State and Local Contracting |  |  |  | 3 | Months
|  | Phase II - Construction Plan /Techncial Specifications |  |  |  | 1 | Months
|  | Phase II - Bidding / Local Procurement |  |  |  | 2 | Months
|  | Phase II - Construction / Installation |  |  |  | 11 | Months
|  | Phase II - Local Inspections / Compliance |  |  |  | 2 | Months
|  | Phase II - State Final Inspections / Compliance |  |  |  | 3 | Months
|  | Phase II - Closeout Compliance |  |  |  | 2 | Months
24
[6 empty] | 36 | Months

## PH II - Summary
I. | Funding Sources (round figures to the nearest dollar) | [5 empty] | ID# 4673-DR-FL
Phase II
| The maximum FEMA share for HMGP/FMA projects is 75%. The other 25% can be made up of State and Local funds as well as in-kind services. Moreover, the FMA program requires that the maximum in-kind match be no more than 12.5 % of the total projects costs. HMGP/FMA funds may be packaged with other Federal Funds, but other Federal funds (except for Federal funds which lose their Federal identity at the State level - such as CDBG, ARS, HOME) may not be used for the State or Local match. | [7 empty] | Awarded Amount | Increase / Decrease
ADJ
1 | Estimated FEMA Share |  |  | 678326.55 | 75% | % of Total | (maximum of 75%) | 0 |  | 678326.55
2 | Non-Federal Share
3 |  | Estimated Local Share |  | 226108.85 | 25% | % of Total | (Cash) | 0 | 0 | 226108.85
4 |  |  |  | 0 | 0% | % of Total | (In-Kind*) | 0 | 0 | 0
5 |  |  |  | 0 | 0% | % of Total | (In-House***) | 0 | 0 | 0
6 |  |  |  | 0 | 0% | % of Total | (Global Match**) | 0 | 0 | 0
7 | Other Agency Share |  |  | 0 | 0% | % of Total |  | 0 | 0 | 0
(Identify Other Non-Federal Agency and availability date)
0
0
8 | Total Funding sources from above |  |  | 904435.4 | 100% | Total % | (should equal 100%) | 0 | 0 | 904435.4
** Identify proposed eligible activities directly related to project to be considered for In-Kind (donated) services
*** Identify proposed eligible activities directly related to project to be considered for In-House services
**** Separate project applications must be submitted for each project (Global) Match project.
Global Match Project # and title:
9 | Total Estimated SR Management Costs |  | Requested | 0 |  |  |  |  | 0 | 0
|  |  | Available | 45221.77 | 5% | of Total | (Max Allowed)
|  |  |  | 45221.77 | If negative - revise SR Mgmt Costs - tab |  |  |  | 0 | 904435.4
J. | Project Milestones/Schedule of Work
List the major milestones in this project by providing an estimate time-line for the critical activities not to exceed a period of 36-month of performance. (e.g. Designing, Engineering, Permitting, etc.)
|  | Milestone |  |  | Number of Days to Complete
|  | Phase I - State and Local Contracting |  |  |  | 2 | Months
|  | Phase I - Bidding / Local Procurement |  |  |  | 2 | Months
|  | Phase I - Design Specifications |  |  |  | 4 | Months
|  | Phase I - Permitting |  |  |  | 2 | Months
|  | Phase I - Deliverables submittal to FDEM |  |  |  | 2 | Months
12
|  | Phase II - State and Local Contracting |  |  |  | 3 | Months
|  | Phase II - Construction Plan /Techncial Specifications |  |  |  | 1 | Months
|  | Phase II - Bidding / Local Procurement |  |  |  | 2 | Months
|  | Phase II - Construction / Installation |  |  |  | 11 | Months
|  | Phase II - Local Inspections / Compliance |  |  |  | 2 | Months
|  | Phase II - State Final Inspections / Compliance |  |  |  | 3 | Months
|  | Phase II - Closeout Compliance |  |  |  | 2 | Months
24
[6 empty] | 36 | Months

## SR Mgmt Costs - Ph I
ID# 4673-DR-FL
G. | Sub-Recipient Management Costs
Based on the amount of federal share being requested in Part F, your project is eligible for up to an additional 5% of the project costs for Sub-Recipient Management Costs. Please indicate below whether or not you would like to request these funds and follow the directions for your selected choice. In addition a Request Form is Required.
Total Estimated Project Costs (Budget F.) | [6 empty] | 450413.94
5%
Total Estimated SR Management Costs Available (5% of Total Project Costs) | [6 empty] | 22520.697 | SRMC Estimated Available
Note: This number will be generated automatically after Budget line items are completed
| YES | I would like to requests these funds (please fill out the itemized table below, then continue to Part I)*
| NO | I do not wish to request these funds. (continue to Part I)*
| Descriptions of SRMC |  |  |  | Qty | Rate | Cost
| Phase I SRMC (per SRMC Request Form) | [6 empty] | Year 1 | Year 2 | Year 3 | TOTAL
1 | Ph I - SRMC Application development (Pre-Award)
2 | Ph I - Pre-Award - Personnel (Sub-Recipient In-House) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Ph I - Pre-Award - Contractual Services |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Ph I - Personnel (Sub-Recipient In-House) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Ph I - Contractual Services |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Ph I - Indirect Costs |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | [6 empty] | 0 | 0 | 0 | 0 | 0
8 | [6 empty] | 0 |  |  |  | 0
9 | [6 empty] | 0 |  |  |  | 0
10 | [6 empty] | 0 |  |  |  | 0
11 | [6 empty] | 0 |  |  |  | 0
12 | [6 empty] | 0 |  |  |  | 0
| Sub-Total of Phase I SRMC | [5 empty] | 0 | 0 | 0 | 0 | 0
| Non-Phased or Phase II SRMC (per SRMC Request Form) | [6 empty] | Year 1 | Year 2 | Year 3 | TOTAL
1 | SRMC Application development (Non-Phased Pre-Award)
2 | Pre-Award - Personnel (Sub-Recipient In-House) | [5 empty] | 0 |  |  |  | 0
3 | Pre-Award - Contractual Services | [5 empty] | 0 |  |  |  | 0
4 | Personnel (Sub-Recipient In-House) | [5 empty] | 0 |  |  |  | 0
5 | Contractual Services | [5 empty] | 0 |  |  |  | 0
6 | Indirect Costs | [5 empty] | 0 |  |  |  | 0
7 | [6 empty] | 0 |  |  |  | 0
8 | [6 empty] | 0 |  |  |  | 0
9 | [6 empty] | 0 |  |  |  | 0
10 | [6 empty] | 0 |  |  |  | 0
11 | [6 empty] | 0 |  |  |  | 0
| Sub-Total of Non-Phased or Phase II SRMC | [5 empty] | 0 | 0 | 0 | 0 | 0
H. |  |  | Total Estimated SRMC Requested |  |  |  | 0 |  |  |  | 0
[6 empty] | Difference | 22520.697 | If negative - you have requested too much - Revise Requested costs
Note: By selecting either “yes” or “no” the Sub-Applicant / Sub-Recipient is acknowledging that they understand what is being offered to them as it is described in this application.
All costs must be reasonable, allowable, allocable, and necessary as required by 2 CFR Part 200 Subpart E, applicable program regulations, and HMA Guidance (2015)
|  |  |  | Maximum SRMC: |  |  | 22520.697
HMGP Management Costs (Interim) Policy # 104-11-1 FAQ, March 23, 2020
Typically, a non-construction budget for management costs will include but the following cost categories: personnel, fringe benefits, travel, equipment, supplies, contractual, and indirect costs. A brief narrative may be required to identify what the funds will be used for. These are required fields in the Application.
Administrative costs are expenses incurred by a recipient or a subrecipient in managing and administering the federal award to ensure that federal, state, or tribal requirements are met including:
• solicitation, development, review, and processing of the actual SRMC subapplication
NOTE: only cost allowed for Pre-Award SRMC - completing the SRMC Request form
• delivery of technical assistance;
• quarterly progress and fiscal reporting;
• project monitoring;
• technical monitoring;
• compliance activities associated with federal procurement requirements;
• documentation of quality of work verification for quarterly reports and closeout;
• payment of claims;
• closeout review and liquidation; and
• records retention.

## SR Mgmt Costs - Ph II
ID# 4673-DR-FL
G. | Sub-Recipient Management Costs
Based on the amount of federal share being requested in Part F, your project is eligible for up to an additional 5% of the project costs for Sub-Recipient Management Costs. Please indicate below whether or not you would like to request these funds and follow the directions for your selected choice. In addition a Request Form is Required.
Total Estimated Project Costs (Budget F.) | [6 empty] | 904435.4
5%
Total Estimated SR Management Costs Available (5% of Total Project Costs) | [6 empty] | 45221.77 | SRMC Estimated Available
Note: This number will be generated automatically after Budget line items are completed
| YES | I would like to requests these funds (please fill out the itemized table below, then continue to Part I)*
| NO | I do not wish to request these funds. (continue to Part I)*
| Descriptions of SRMC |  |  |  | Qty | Rate | Cost
| Phase I SRMC (per SRMC Request Form) | [6 empty] | Year 1 | Year 2 | Year 3 | TOTAL
1 | Ph I - SRMC Application development (Pre-Award)
2 | Ph I - Pre-Award - Personnel (Sub-Recipient In-House) | [5 empty] | 0 |  |  |  | 0
3 | Ph I - Pre-Award - Contractual Services | [5 empty] | 0 |  |  |  | 0
4 | Ph I - Personnel (Sub-Recipient In-House) | [5 empty] | 0 |  |  |  | 0
5 | Ph I - Contractual Services | [5 empty] | 0 |  |  |  | 0
6 | Ph I - Indirect Costs | [5 empty] | 0 |  |  |  | 0
7 | [6 empty] | 0 |  |  |  | 0
8 | [6 empty] | 0 |  |  |  | 0
9 | [6 empty] | 0 |  |  |  | 0
10 | [6 empty] | 0 |  |  |  | 0
11 | [6 empty] | 0 |  |  |  | 0
12 | [6 empty] | 0 |  |  |  | 0
| Sub-Total of Phase I SRMC | [5 empty] | 0 | 0 | 0 | 0 | 0
| Non-Phased or Phase II SRMC (per SRMC Request Form) | [6 empty] | Year 1 | Year 2 | Year 3 | TOTAL
1 | SRMC Application development (Non-Phased Pre-Award)
2 | Pre-Award - Personnel (Sub-Recipient In-House) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Pre-Award - Contractual Services |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Personnel (Sub-Recipient In-House) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Contractual Services |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Indirect Costs |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  |  |  |  | 0 |  | 0 |  |  |  | 0
9 |  |  |  |  | 0 |  | 0 |  |  |  | 0
10 |  |  |  |  | 0 |  | 0 |  |  |  | 0
11 |  |  |  |  | 0 |  | 0 |  |  |  | 0
| Sub-Total of Non-Phased or Phase II SRMC | [5 empty] | 0 | 0 | 0 | 0 | 0
H. |  |  | Total Estimated SRMC Requested |  |  |  | 0 |  |  |  | 0
[6 empty] | Difference | 45221.77 | If negative - you have requested too much - Revise Requested costs
Note: By selecting either “yes” or “no” the Sub-Applicant / Sub-Recipient is acknowledging that they understand what is being offered to them as it is described in this application.
All costs must be reasonable, allowable, allocable, and necessary as required by 2 CFR Part 200 Subpart E, applicable program regulations, and HMA Guidance (2015)
|  |  |  | Maximum SRMC: |  |  | 45221.77
HMGP Management Costs (Interim) Policy # 104-11-1 FAQ, March 23, 2020
Typically, a non-construction budget for management costs will include but the following cost categories: personnel, fringe benefits, travel, equipment, supplies, contractual, and indirect costs. A brief narrative may be required to identify what the funds will be used for. These are required fields in the Application.
Administrative costs are expenses incurred by a recipient or a subrecipient in managing and administering the federal award to ensure that federal, state, or tribal requirements are met including:
• solicitation, development, review, and processing of the actual SRMC subapplication
NOTE: only cost allowed for Pre-Award SRMC - completing the SRMC Request form
• delivery of technical assistance;
• quarterly progress and fiscal reporting;
• project monitoring;
• technical monitoring;
• compliance activities associated with federal procurement requirements;
• documentation of quality of work verification for quarterly reports and closeout;
• payment of claims;
• closeout review and liquidation; and
• records retention.

## Line Item transfer
ID# 4673-DR-FL
Cost Categories | Project Cost | 75% | Non-Federal Share | Revised Date | Justification
Federal Share
MATERIALS
Materials Approved: | 904435.4 | 678326.55 | 226108.85
Line item transfer #1 to/from _____ | 0 | 0 | 0
Line item transfer #2 to/from _____ | 0 | 0 | 0
Line item transfer #3 to/from _____ | 0 | 0 | 0
REVISED MATERIALS | 904435.4 | 678326.55 | 226108.85
LABOR
Labor Approved: | 135200 | 101400 | 33800
Line item transfer #1 to/from _____ | 0 | 0 | 0
Line item transfer #2 to/from _____ | 0 | 0 | 0
Line item transfer #3 to/from _____ | 0 | 0 | 0
REVISED LABOR | 135200 | 101400 | 33800
FEES
Fees Approved | 0 | 0 | 0
Line item transfer #1 to/from _____ | 0 | 0 | 0
Line item transfer #2 to/from _____ | 0 | 0 | 0
Line item transfer #3 to/from _____ | 0 | 0 | 0
REVISED FEES | 0 | 0 | 0
PRE-AWARD |  |  |  |  | NOTE: Pre-Award cannot be increased without approval from FEMA
Pre-Award Approved: | 0 | 0 | 0
Line item transfer #1 to/from _____ | 0 | 0 | 0
Line item transfer #2 to/from _____ | 0 | 0 | 0
Line item transfer #3 to/from _____ | 0 | 0 | 0
REVISED PRE-AWARD | 0 | 0 | 0
Contingency Approved: | 0 | 0 | 0
Line item transfer #1 to/from _____ | 0 | 0 | 0
Line item transfer #2 to/from _____ | 0 | 0 | 0
Line item transfer #3 to/from _____ | 0 | 0 | 0
REVISED CONTINGENCY | 0 | 0 | 0
Initial Agreement Amount: | 1039635.4 | 779726.55 | 259908.85
Approved Costs | 1039635.4 | 779726.55 | 0
Line item transfer #1 - check | 0 | 0 | 0 |  | should be zero
Line item transfer #2 - check | 0 | 0 | 0 |  | should be zero
Line item transfer #3 - check | 0 | 0 | 0 |  | should be zero
Project Total: | 1039635.4 | 779726.55 | 259908.85
*Any line item amount in this Budget may be increased or decreased 10% or less, with the Division’s approval, without an amendment to this Agreement being required, so long as the overall amount of the funds obligated under this Agreement is not increased.
Requested by:
date
Approved by Project Manager:
date

## SRMC-Line Item transfer
Cost Categories | SRMC Cost | 100% | Revised Date | Justification
Federal Share
PERSONNEL (IN-HOUSE)
Personnel Approved: | 0 | 0
Line item transfer #1 to/from _____ | 0 | 0
Line item transfer #2 to/from _____ | 0 | 0
Line item transfer #3 to/from _____ | 0 | 0
REVISED PERSONNEL | 0 | 0
CONTRACTOR
Contractor Approved: | 0 | 0
Line item transfer #1 to/from _____ | 0 | 0
Line item transfer #2 to/from _____ | 0 | 0
Line item transfer #3 to/from _____ | 0 | 0
REVISED CONTRACTOR | 0 | 0
INDIRECT COSTS
Indirect Cost Approved | 0 | 0
Line item transfer #1 to/from _____ | 0 | 0
Line item transfer #2 to/from _____ | 0 | 0
Line item transfer #3 to/from _____ | 0 | 0
REVISED INDIRECT | 0 | 0
Total SRMC | 0 | 0
Approved Costs | #REF! | #REF!
Line item transfer #1 - check | 0 | 0 |  | should be zero
Line item transfer #2 - check | 0 | 0 |  | should be zero
Line item transfer #3 - check | 0 | 0 |  | should be zero
SRMC Total: | 0 | 0
*Any line item amount in this Budget may be increased or decreased 10% or less, with the Division’s approval, without an amendment to this Agreement being required, so long as the overall amount of the funds obligated under this Agreement is not increased.

## Workbook guidance
When completing the Budget sheets ALL PROJECT COSTS WILL BE ROUNDED TO THE NEAREST DOLLAR - NO CENTS Contingency Costs will be rounded down - no cents 3/30/22
In order to assist applicants with filling out the following Budget section, we have provided the following instructions for your convenience. For this section, we ask that you provide details of all the estimated costs of the project, as it is used for the benefit-costs analysis as well as for the feasibility and effectiveness review.
Complete the Budget Sheet and the SR Mgmt. Costs sheet - the other sheets will automatically format. If you have a Code-Plus project - utilize the last sheet to provide the required costs. If you are applying for an Acquisition detailed budgets per property is required.
For the cost sections relating to Materials, Labor, and Fees, it is important to note,
Lump sums without supporting documentation showing a breakdown of those costs are not acceptable. For those items that will not fit in the spaces provided, attach the appropriate documentation to your application.
Sub-Total cells will auto sum the costs in their respective Sections (Cost columns).
Do not factor Sub-Recipient Management Costs (SRMC) into sections A-C. If SRMC are being requested, see part G. In addition, complete the SRMC Request-MOD form for all details.
Contingency Costs need to be justified and reported as a separate line item in part E of this section. From left to right in that part, enter the desired percentage (maximum 5%), the amount the percentage is to be applied to, and the resulting amount. PLEASE NOTE- These cells will auto-calculate across the row and will be calculated into the Final Estimated Project Cost below it. Take care that everything is calculated correctly. (Adjust down to whole dollar (cents) in cell G106, and/or G107).
Pre-Award Costs: costs must be identified as a separate line item, AND a completed HMGP Pre-Award Cost Request Form MUST be submitted with this application, detailing the items/cost and requested start date.
Mark all In-kind (donated) services with (**); In-house (employee) services with (***), per each line item.
All funding sources (In-kind, In-house, Global Match, and Other Agencies) must be identified AND documentation submitted, and also identified on the Funding Sources - Section I – (Funding Summary Tab).
For SRMC, in compliance with Disaster Relief and Recovery Act of 2018 (DRRA) and the subsequent FEMA Interim Policy #104-11-1, the Florida Division of Emergency Management has included a section for applicants to request, or refuse, SRMC funds that are available to them. Under this new policy, HMGP projects awarded under disasters declared on or after August 1, 2017, are eligible for SRMC up to 5 percent of their total project costs.
Applicants choosing to apply for this funding must detail the specific administrative costs in Part G of this section. These costs must be eligible administrative costs, conforming to the requirements set in 2 CFR Part 200 Subpart E. Applicants must ensure that their administrative costs are reasonable, allowable, allocable, and necessary for the performance of the federal award.
The State will allot these SRMC on a project-by-project basis up to 5 percent of the total project cost. An applicant may request less than this, but no higher. These SRMC will be considered a separate pool of funding and WILL NOT affect a project’s benefit-cost analysis.
Sub-Recipient Management Costs will be reimbursed per reimbursement request, and no more than 5 percent of any given project cost reimbursement request amount. All SRMC reimbursements will be contingent upon adequate documentation from the sub-recipient.
Documentation MUST be invoiced separately and not comingled with the project costs.
Sub-Recipient Management costs will be reimbursed at 100 percent of the amount of management costs requested, so far as they are adequately documented and are no more than 5 percent of the actual project cost Request for Reimbursement (RFR). Any unused management costs at closeout following the final payment will be de-obligated. If the final total project cost results in an under-run, management costs will be reduced accordingly.
If additional rows are needed - please contact HMGP by phone or email