## Group 1
Group 1
| Year 1 Total Dredging Costs | Year 5 Total Dredging Costs | Five-Year Average Annual
Insurance/Bonding | 8174.5907 | 10041.5284 | 2008.3057
Mob/Demob (LS) | 505942.4491 | 621491.1086 | 124298.2217
Dredging & Placement (CY) | 583536.893 | 716806.8051 | 143361.361
Environmental Protection | 43181.7301 | 53043.7036 | 10608.7407
Seagrass Transplanting & Monitoring (CY) | 75842.2686 | 93163.3542 | 18632.6708
Engineering Fees - Plans, Design & Specs | 121667.7932 | 149454.65 | 29890.93
Construction Administration | 60833.8966 | 74727.325 | 14945.465
Total Dredging OPC | 1399179.6212 | 1718728.4749 | 343745.695
Annual O&M
Navigational Markers repair & replacement |  |  | 3067.8018
Overhead -- Finance Staff |  |  | 5113.0029
Overhead -- Public Works |  |  | 5113.0029
Total O&M Expenditures |  |  | 13293.8077 |  | costs incurred every year
Misc. Assessment Expenditures
Study & Implementation |  |  | 5279.551
Legal Fees |  |  | 1573.0519
Collection Costs (Property Appraiser @1.5%) |  |  | 5872.2058
Collection Costs (Tax Collector @1.5%) |  |  | 5872.2058
First Class Notice Costs ($1.53 per) |  |  | 184.652
Statutory Discount (@4%) |  |  | 15659.2154
Total Misc. Assessment Expenditures |  |  | 34440.8818 |  | costs incurred every year
Estimated Amount Certified to Tax Collector |  |  | 391480.3845
Units |  |  | 307.8
Annual Rate Per Billing Unit |  |  | 1272
Monthly Rate Per Billing Unit |  |  | 106
Canal Dredging Implementation Strategy
|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Assessment Revenue Realized (certified minus collection costs*) |  |  | 363892.1055 | 363892.1055 | 363892.1055 | 363892.1055 | 363892.1055
Annual O&M** |  |  | 20146.4106 | 20146.4106 | 20146.4106 | 20146.4106 | 20146.4106
Remaining Capital |  |  | 343745.695 | 343745.695 | 343745.695 | 343745.695 | 343745.695
Insurance/Bonding | [5 empty] | 5020.7642 | 5020.7642 | start in year 4; finish in year 5
Mob/Demob (LS) | [5 empty] | 310745.5543 | 310745.5543 | start in year 4; finish in year 5
Dredging & Placement (CY) | [5 empty] | 358403.4025 | 358403.4025 | start in year 4; finish in year 5
Environmental Protection |  |  |  | 53043.7036
Seagrass Transplanting & Monitoring (CY) |  |  |  | 93163.3542
Engineering Fees - Plans, Design & Specs |  |  | 121667.7932
Construction Administration | [6 empty] | 74727.325
Total Dredging Costs |  |  | 121667.7932 | 146207.0578 | 0 | 674169.721 | 748897.046
Additional Revenue for Reserve |  |  | 222077.9018 | 197538.6372 | 343745.695 | -330424.0261 | -405151.3511
Total Reserve in Bank |  |  | 222077.9018 | 419616.539 | 763362.234 | 432938.2079 | 27786.8568
*Collection Costs Include
Property Appraiser Costs
Tax Collector Costs
Statutory Discount
Notice Costs
**Annual O&M Includes
Navigational Markers Repair & Replacement
Staffing Overhead
Assessment Roll Maintenance
Legal

## Group 2
Group 2
| Year 1 Total Dredging Costs | Year 5 Total Dredging Costs | Five-Year Average Annual
Insurance/Bonding | 9683.4044 | 11894.9295 | 2378.9859
Mob/Demob (LS) | 637112.7137 | 782618.4331 | 156523.6866
Dredging & Placement (CY) | 691242.4027 | 849110.4233 | 169822.0847
Environmental Protection | 51151.9378 | 62834.1713 | 12566.8343
Seagrass Transplanting & Monitoring (CY) | 94136.5022 | 115635.68 | 23127.136
Engineering Fees - Plans, Design & Specs | 148332.6961 | 182209.3637 | 36441.8727
Construction Administration | 74166.348 | 91104.6819 | 18220.9364
Total Dredging OPC | 1705826.0049 | 2095407.6827 | 419081.5365
Annual O&M
Navigational Markers repair & replacement |  |  | 4790.0764
Overhead -- Finance Staff |  |  | 7983.4607
Overhead -- Public Works |  |  | 7983.4607
Total O&M Expenditures |  |  | 20756.9979 |  | costs incurred every year
Misc. Assessment Expenditures
Study & Implementation |  |  | 8243.5094
Legal Fees |  |  | 2456.1688
Collection Costs (Property Appraiser @1.5%) |  |  | 7270.6712
Collection Costs (Tax Collector @1.5%) |  |  | 7270.6712
First Class Notice Costs ($1.53 per) |  |  | 243.404
Statutory Discount (@4%) |  |  | 19388.4566
Total Misc. Assessment Expenditures |  |  | 44872.8814 |  | costs incurred every year
Estimated Amount Certified to Tax Collector |  |  | 484711.4158
Units |  |  | 409.45
Annual Rate Per Billing Unit |  |  | 1184
Monthly Rate Per Billing Unit |  |  | 98.6667
Canal Dredging Implementation Strategy
|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Assessment Revenue Realized (certified minus collection costs*) |  |  | 450538.2127 | 450538.2127 | 450538.2127 | 450538.2127 | 450538.2127
Annual O&M** |  |  | 31456.6762 | 31456.6762 | 31456.6762 | 31456.6762 | 31456.6762
Remaining Capital |  |  | 419081.5365 | 419081.5365 | 419081.5365 | 419081.5365 | 419081.5365
Insurance/Bonding | [5 empty] | 5947.4647 | 5947.4647 | start in year 4; finish in year 5
Mob/Demob (LS) | [5 empty] | 391309.2165 | 391309.2165 | start in year 4; finish in year 5
Dredging & Placement (CY) | [5 empty] | 424555.2117 | 424555.2117 | start in year 4; finish in year 5
Environmental Protection |  |  |  | 62834.1713
Seagrass Transplanting & Monitoring (CY) |  |  |  | 115635.68
Engineering Fees - Plans, Design & Specs |  |  | 148332.6961
Construction Administration | [6 empty] | 91104.6819
Total Dredging Costs |  |  | 148332.6961 | 178469.8513 | 0 | 821811.8929 | 912916.5748
Additional Revenue for Reserve |  |  | 270748.8405 | 240611.6853 | 419081.5365 | -402730.3564 | -493835.0383
Total Reserve in Bank |  |  | 270748.8405 | 511360.5257 | 930442.0623 | 527711.7059 | 33876.6676
*Collection Costs Include
Property Appraiser Costs
Tax Collector Costs
Statutory Discount
Notice Costs
**Annual O&M Includes
Navigational Markers Repair & Replacement
Staffing Overhead
Assessment Roll Maintenance
Legal

## Group 3
Group 3
| Year 1 Total Dredging Costs | Year 5 Total Dredging Costs | Five-Year Average Annual
Insurance/Bonding | 2065.0066 | 2536.619 | 507.3238
Mob/Demob (LS) | 449726.6214 | 552436.541 | 110487.3082
Dredging & Placement (CY) | 147408.9126 | 181074.6038 | 36214.9208
Environmental Protection | 10908.2595 | 13399.5207 | 2679.9041
Seagrass Transplanting & Monitoring (CY) | 16476.0835 | 20238.941 | 4047.7882
Engineering Fees - Plans, Design & Specs | 62658.4884 | 76968.6225 | 15393.7245
Construction Administration | 31329.2442 | 38484.3113 | 7696.8623
Total Dredging OPC | 720572.6162 | 885139.1593 | 177027.8319
Annual O&M
Navigational Markers repair & replacement |  |  | 2260.4855
Overhead -- Finance Staff |  |  | 3767.4759
Overhead -- Public Works |  |  | 3767.4759
Total O&M Expenditures |  |  | 9795.4372 |  | costs incurred every year
Misc. Assessment Expenditures
Study & Implementation |  |  | 3890.1955
Legal Fees |  |  | 1159.0909
Collection Costs (Property Appraiser @1.5%) |  |  | 3097.2527
Collection Costs (Tax Collector @1.5%) |  |  | 3097.2527
First Class Notice Costs ($1.53 per) |  |  | 157.112
Statutory Discount (@4%) |  |  | 8259.3405
Total Misc. Assessment Expenditures |  |  | 19660.2443 |  | costs incurred every year
Estimated Amount Certified to Tax Collector |  |  | 206483.5134
Units |  |  | 70.11
Annual Rate Per Billing Unit |  |  | 2946
Monthly Rate Per Billing Unit |  |  | 245.5
Canal Dredging Implementation Strategy
|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Assessment Revenue Realized (certified minus collection costs*) |  |  | 191872.5554 | 191872.5554 | 191872.5554 | 191872.5554 | 191872.5554
Annual O&M** |  |  | 14844.7236 | 14844.7236 | 14844.7236 | 14844.7236 | 14844.7236
Remaining Capital |  |  | 177027.8319 | 177027.8319 | 177027.8319 | 177027.8319 | 177027.8319
Insurance/Bonding | [5 empty] | 1268.3095 | 1268.3095 | start in year 4; finish in year 5
Mob/Demob (LS) | [5 empty] | 276218.2705 | 276218.2705 | start in year 4; finish in year 5
Dredging & Placement (CY) | [5 empty] | 90537.3019 | 90537.3019 | start in year 4; finish in year 5
Environmental Protection |  |  |  | 13399.5207
Seagrass Transplanting & Monitoring (CY) |  |  |  | 20238.941
Engineering Fees - Plans, Design & Specs |  |  | 62658.4884
Construction Administration | [6 empty] | 38484.3113
Total Dredging Costs |  |  | 62658.4884 | 33638.4617 | 0 | 368023.8819 | 406508.1932
Additional Revenue for Reserve |  |  | 114369.3435 | 143389.3702 | 177027.8319 | -190996.05 | -229480.3613
Total Reserve in Bank |  |  | 114369.3435 | 257758.7137 | 434786.5456 | 243790.4955 | 14310.1342
*Collection Costs Include
Property Appraiser Costs
Tax Collector Costs
Statutory Discount
Notice Costs
**Annual O&M Includes
Navigational Markers Repair & Replacement
Staffing Overhead
Assessment Roll Maintenance
Legal

## Group 4
Group 4
| Year 1 Total Dredging Costs | Year 5 Total Dredging Costs | Five-Year Average Annual
Insurance/Bonding | 10970.1394 | 13475.5329 | 2695.1066
Mob/Demob (LS) | 484861.5137 | 595595.6458 | 119119.1292
Dredging & Placement (CY) | 783094.9913 | 961940.5826 | 192388.1165
Environmental Protection | 57949.0294 | 71183.6031 | 14236.7206
Seagrass Transplanting & Monitoring (CY) | 146433.5158 | 179876.4429 | 35975.2886
Engineering Fees - Plans, Design & Specs | 148330.919 | 182207.1807 | 36441.4361
Construction Administration | 74165.4595 | 91103.5904 | 18220.7181
Total Dredging OPC | 1705805.568 | 2095382.5784 | 419076.5157
Annual O&M
Navigational Markers repair & replacement |  |  | 5086.0924
Overhead -- Finance Staff |  |  | 8476.8207
Overhead -- Public Works |  |  | 8476.8207
Total O&M Expenditures |  |  | 22039.7337 |  | costs incurred every year
Misc. Assessment Expenditures
Study & Implementation |  |  | 8752.9398
Legal Fees |  |  | 2607.9545
Collection Costs (Property Appraiser @1.5%) |  |  | 7302.1072
Collection Costs (Tax Collector @1.5%) |  |  | 7302.1072
First Class Notice Costs ($1.53 per) |  |  | 253.502
Statutory Discount (@4%) |  |  | 19472.2858
Total Misc. Assessment Expenditures |  |  | 45690.8965 |  | costs incurred every year
Estimated Amount Certified to Tax Collector |  |  | 486807.1459
Units |  |  | 166.25
Annual Rate Per Billing Unit |  |  | 2929
Monthly Rate Per Billing Unit |  |  | 244.0833
Canal Dredging Implementation Strategy
|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Assessment Revenue Realized (certified minus collection costs*) |  |  | 452477.1437 | 452477.1437 | 452477.1437 | 452477.1437 | 452477.1437
Annual O&M** |  |  | 33400.6281 | 33400.6281 | 33400.6281 | 33400.6281 | 33400.6281
Remaining Capital |  |  | 419076.5157 | 419076.5157 | 419076.5157 | 419076.5157 | 419076.5157
Insurance/Bonding | [5 empty] | 6737.7664 | 6737.7664 | start in year 4; finish in year 5
Mob/Demob (LS) | [5 empty] | 297797.8229 | 297797.8229 | start in year 4; finish in year 5
Dredging & Placement (CY) | [5 empty] | 480970.2913 | 480970.2913 | start in year 4; finish in year 5
Environmental Protection |  |  |  | 71183.6031
Seagrass Transplanting & Monitoring (CY) |  |  |  | 179876.4429
Engineering Fees - Plans, Design & Specs |  |  | 148330.919
Construction Administration | [6 empty] | 91103.5904
Total Dredging Costs |  |  | 148330.919 | 251060.046 | 0 | 785505.8806 | 876609.471
Additional Revenue for Reserve |  |  | 270745.5967 | 168016.4697 | 419076.5157 | -366429.365 | -457532.9553
Total Reserve in Bank |  |  | 270745.5967 | 438762.0664 | 857838.5821 | 491409.2171 | 33876.2618
*Collection Costs Include
Property Appraiser Costs
Tax Collector Costs
Statutory Discount
Notice Costs
**Annual O&M Includes
Navigational Markers Repair & Replacement
Staffing Overhead
Assessment Roll Maintenance
Legal

## Group 5
Group 5
| Year 1 Total Dredging Costs | Year 5 Total Dredging Costs | Five-Year Average Annual
Insurance/Bonding | 7181.9187 | 8822.147 | 1764.4294
Mob/Demob (LS) | 469402.1611 | 576605.6397 | 115321.1279
Dredging & Placement (CY) | 512675.7635 | 629762.1975 | 125952.4395
Environmental Protection | 37938.0065 | 46602.4026 | 9320.4805
Seagrass Transplanting & Monitoring (CY) | 58719.0448 | 72129.477 | 14425.8954
Engineering Fees - Plans, Design & Specs | 108591.6895 | 133392.1864 | 26678.4373
Construction Administration | 54295.8447 | 66696.0932 | 13339.2186
Total Dredging OPC | 1248804.4288 | 1534010.1434 | 306802.0287
Annual O&M
Navigational Markers repair & replacement |  |  | 9822.3478
Overhead -- Finance Staff |  |  | 16370.5796
Overhead -- Public Works |  |  | 16370.5796
Total O&M Expenditures |  |  | 42563.507 |  | costs incurred every year
Misc. Assessment Expenditures
Study & Implementation |  |  | 16903.8255
Legal Fees |  |  | 5036.526
Collection Costs (Property Appraiser @1.5%) |  |  | 5995.4993
Collection Costs (Tax Collector @1.5%) |  |  | 5995.4993
First Class Notice Costs ($1.53 per) |  |  | 415.07
Statutory Discount (@4%) |  |  | 15987.9982
Total Misc. Assessment Expenditures |  |  | 50334.4182 |  | costs incurred every year
Estimated Amount Certified to Tax Collector |  |  | 399699.9539
Units |  |  | 524.4
Annual Rate Per Billing Unit |  |  | 763
Monthly Rate Per Billing Unit |  |  | 63.5833
Canal Dredging Implementation Strategy
|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Assessment Revenue Realized (certified minus collection costs*) |  |  | 371305.8871 | 371305.8871 | 371305.8871 | 371305.8871 | 371305.8871
Annual O&M** |  |  | 64503.8584 | 64503.8584 | 64503.8584 | 64503.8584 | 64503.8584
Remaining Capital |  |  | 306802.0287 | 306802.0287 | 306802.0287 | 306802.0287 | 306802.0287
Insurance/Bonding | [5 empty] | 4411.0735 | 4411.0735 | start in year 4; finish in year 5
Mob/Demob (LS) | [5 empty] | 288302.8198 | 288302.8198 | start in year 4; finish in year 5
Dredging & Placement (CY) | [5 empty] | 314881.0988 | 314881.0988 | start in year 4; finish in year 5
Environmental Protection |  |  |  | 46602.4026
Seagrass Transplanting & Monitoring (CY) |  |  |  | 72129.477
Engineering Fees - Plans, Design & Specs |  |  | 108591.6895
Construction Administration | [6 empty] | 66696.0932
Total Dredging Costs |  |  | 108591.6895 | 118731.8796 | 0 | 607594.9921 | 674291.0853
Additional Revenue for Reserve |  |  | 198210.3392 | 188070.149 | 306802.0287 | -300792.9634 | -367489.0566
Total Reserve in Bank |  |  | 198210.3392 | 386280.4882 | 693082.5169 | 392289.5535 | 24800.4969
*Collection Costs Include
Property Appraiser Costs
Tax Collector Costs
Statutory Discount
Notice Costs
**Annual O&M Includes
Navigational Markers Repair & Replacement
Staffing Overhead
Assessment Roll Maintenance
Legal

## Group 6
Group 6
| Year 1 Total Dredging Costs | Year 5 Total Dredging Costs | Five-Year Average Annual
Insurance/Bonding | 9192.1762 | 11291.5131 | 2258.3026
Mob/Demob (LS) | 642466.6021 | 789195.0586 | 157839.0117
Dredging & Placement (CY) | 656176.4524 | 806036.0058 | 161207.2012
Environmental Protection | 48557.0575 | 59646.6644 | 11929.3329
Seagrass Transplanting & Monitoring (CY) | 105957.6078 | 130156.5252 | 26031.305
Engineering Fees - Plans, Design & Specs | 146234.9896 | 179632.5767 | 35926.5153
Construction Administration | 73117.4948 | 89816.2884 | 17963.2577
Total Dredging OPC | 1681702.3804 | 2065774.6322 | 413154.9264
Annual O&M
Navigational Markers repair & replacement |  |  | 5355.1978
Overhead -- Finance Staff |  |  | 8925.3297
Overhead -- Public Works |  |  | 8925.3297
Total O&M Expenditures |  |  | 23205.8572 |  | costs incurred every year
Misc. Assessment Expenditures
Study & Implementation |  |  | 9216.0583
Legal Fees |  |  | 2745.9416
Collection Costs (Property Appraiser @1.5%) |  |  | 7235.2494
Collection Costs (Tax Collector @1.5%) |  |  | 7235.2494
First Class Notice Costs ($1.53 per) |  |  | 262.682
Statutory Discount (@4%) |  |  | 19293.9985
Total Misc. Assessment Expenditures |  |  | 45989.1792 |  | costs incurred every year
Estimated Amount Certified to Tax Collector |  |  | 482349.9629
Units |  |  | 551.95
Annual Rate Per Billing Unit |  |  | 874
Monthly Rate Per Billing Unit |  |  | 72.8333
Canal Dredging Implementation Strategy
|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Assessment Revenue Realized (certified minus collection costs*) |  |  | 448322.7835 | 448322.7835 | 448322.7835 | 448322.7835 | 448322.7835
Annual O&M** |  |  | 35167.8571 | 35167.8571 | 35167.8571 | 35167.8571 | 35167.8571
Remaining Capital |  |  | 413154.9264 | 413154.9264 | 413154.9264 | 413154.9264 | 413154.9264
Insurance/Bonding | [5 empty] | 5645.7565 | 5645.7565 | start in year 4; finish in year 5
Mob/Demob (LS) | [5 empty] | 394597.5293 | 394597.5293 | start in year 4; finish in year 5
Dredging & Placement (CY) | [5 empty] | 403018.0029 | 403018.0029 | start in year 4; finish in year 5
Environmental Protection |  |  |  | 59646.6644
Seagrass Transplanting & Monitoring (CY) |  |  |  | 130156.5252
Engineering Fees - Plans, Design & Specs |  |  | 146234.9896
Construction Administration | [6 empty] | 89816.2884
Total Dredging Costs |  |  | 146234.9896 | 189803.1896 | 0 | 803261.2887 | 893077.5771
Additional Revenue for Reserve |  |  | 266919.9368 | 223351.7368 | 413154.9264 | -390106.3623 | -479922.6507
Total Reserve in Bank |  |  | 266919.9368 | 490271.6736 | 903426.6001 | 513320.2378 | 33397.5871
*Collection Costs Include
Property Appraiser Costs
Tax Collector Costs
Statutory Discount
Notice Costs
**Annual O&M Includes
Navigational Markers Repair & Replacement
Staffing Overhead
Assessment Roll Maintenance
Legal

## Group 7
Group 7
| Year 1 Total Dredging Costs | Year 5 Total Dredging Costs | Five-Year Average Annual
Insurance/Bonding | 1978.7348 | 2430.6442 | 486.1288
Mob/Demob (LS) | 337294.9661 | 414327.4057 | 82865.4811
Dredging & Placement (CY) | 141250.4691 | 173509.6764 | 34701.9353
Environmental Protection | 10452.5347 | 12839.7161 | 2567.9432
Seagrass Transplanting & Monitoring (CY) | 30895.3311 | 37951.2998 | 7590.26
Engineering Fees - Plans, Design & Specs | 52187.2036 | 64105.8742 | 12821.1748
Construction Administration | 26093.6018 | 32052.9371 | 6410.5874
Total Dredging OPC | 600152.8411 | 737217.5535 | 147443.5107
Annual O&M
Navigational Markers repair & replacement |  |  | 2771.7858
Overhead -- Finance Staff |  |  | 4619.643
Overhead -- Public Works |  |  | 4619.643
Total O&M Expenditures |  |  | 12011.0718 |  | costs incurred every year
Misc. Assessment Expenditures
Study & Implementation |  |  | 4770.1206
Legal Fees |  |  | 1421.2662
Collection Costs (Property Appraiser @1.5%) |  |  | 2674.5246
Collection Costs (Tax Collector @1.5%) |  |  | 2674.5246
First Class Notice Costs ($1.53 per) |  |  | 174.554
Statutory Discount (@4%) |  |  | 7132.0655
Total Misc. Assessment Expenditures |  |  | 18847.0555 |  | costs incurred every year
Estimated Amount Certified to Tax Collector |  |  | 178301.638
Units |  |  | 23.655
Annual Rate Per Billing Unit |  |  | 7538
Monthly Rate Per Billing Unit |  |  | 628.1667
Canal Dredging Implementation Strategy
|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Assessment Revenue Realized (certified minus collection costs*) |  |  | 165645.9694 | 165645.9694 | 165645.9694 | 165645.9694 | 165645.9694
Annual O&M** |  |  | 18202.4587 | 18202.4587 | 18202.4587 | 18202.4587 | 18202.4587
Remaining Capital |  |  | 147443.5107 | 147443.5107 | 147443.5107 | 147443.5107 | 147443.5107
Insurance/Bonding | [5 empty] | 1215.3221 | 1215.3221 | start in year 4; finish in year 5
Mob/Demob (LS) | [5 empty] | 207163.7029 | 207163.7029 | start in year 4; finish in year 5
Dredging & Placement (CY) | [5 empty] | 86754.8382 | 86754.8382 | start in year 4; finish in year 5
Environmental Protection |  |  |  | 12839.7161
Seagrass Transplanting & Monitoring (CY) |  |  |  | 37951.2998
Engineering Fees - Plans, Design & Specs |  |  | 52187.2036
Construction Administration | [6 empty] | 32052.9371
Total Dredging Costs |  |  | 52187.2036 | 50791.0158 | 0 | 295133.8632 | 327186.8003
Additional Revenue for Reserve |  |  | 95256.3071 | 96652.4949 | 147443.5107 | -147690.3525 | -179743.2896
Total Reserve in Bank |  |  | 95256.3071 | 191908.802 | 339352.3127 | 191661.9602 | 11918.6706
*Collection Costs Include
Property Appraiser Costs
Tax Collector Costs
Statutory Discount
Notice Costs
**Annual O&M Includes
Navigational Markers Repair & Replacement
Staffing Overhead
Assessment Roll Maintenance
Legal