## Sheet1
Issue | 2022 | 2023 | 2024 | 2025 | 2026 | 2027
Beach Management | Permit Spit Management Plan Greer Island. Initiate short-term plan to remove a portion of spit at entrance to lagoon. Determine estimated cost and timing of long-term sand relocation. | Construct New Pass Structure tightening near November 2023. | Conduct interim nourishment end of calendar 2024/beginning of 2025. Begin Comprehensive Beach Management Plan Update; consider inclusion of structural solution to Gulfside Rd area | Update and Adopt Beach Management Plan. | Advance planning for next referendum and schedule design and construction. | Begin survey, design and permitting next beach nourishment. Plan/budget for referendum amount.
Sea Level Rise - Comprehensive Adaptation Plan | Complete Phases 3 & 4 (Phase 4 is implementation plan - funding strategies would need to be discussed with Commission) | Re-asses Baseline Assumption FY 23/24; Consultant help pursue/explore external funding options for implementation, as needed. Consider programming Continue to program grant matching funds into CIP and pursue grants. Procure Norton Street road elevation design. Re-assess Village area. | Based on available funding, begin any lower cost, early implementation of adaptation strategies within upcoming projects, as applicable (ex., resurfacing, utility projects). Design Norton Street road elevation improvement project. Continue pursuing grant funding for design and implementation of road elevation projects. | Continue pursuing grant funding for implementation of road elevation projects. Depending on funds acquired, begin construction and continue design in Sleepy Lagoon, Buttonwood, and the Village areas. | Continue pursuing grant funding for implementation of road elevation projects. Depending on funds acquired, begin construction and continue design in Sleepy Lagoon, Buttonwood, and the Village areas. | Re-baseline and compare original projetions to current. Town consider additional local funding depending on results of grant efforts.
Subaqueous Force Main | Conduct pipeline assessment. Initiate mainland pipe lining rehab project. Obtain U.S. Army Corps permit for redundant sub-aqueous force main. Negotiate necessary easements. Seek State and Federal appropriations to offset project costs. | Continue to pursue outside funding opportunities. Complete mainland lining project. Complete pipeline assessment. Final assessment of feasibility of mutliple construction methods for sub-aqueous portion under Sarasota Bay. | Final Design & Permitting; additional Easement Acquisition, as needed. | Construction/CEI | Depending on cost savings or remaining budget dolars from larger project, Town consider re-lining the existing sub-aqueous pipeline portion under sarasota Bay as a redundant force main. | Reline existing sub-aqueous force main under bay, pending available funds.
GMD Complete Streets | CCS Turn Lane: work with FDOT on Joint Project Agreement and related design update requirements. Complete design of Broadway Roundabout. Complete GMD Complete Streets Corridor Plan. FDOT initiate pedestrian hybrid beacons (2) design-build project and (1) enhanced RRFB project. | CCS Turn Lane: work with FDOT on Joint Project Agreement. Complete design of Broadway Roundabout. Pursue funding for Broadway Roundabout. Finalize Corridor Plan recommendations and establish a priority list. Pursue more immediate funding for Complete Streets Design elements. Pursue funding options/strategies for multi-purpose trail repair/replacement. | Pursue Identify additional funding source for Broadway Roundabout beyond $1.685 million committed by FDOT. FDOT/ Town construct CCS Turn Lane improvement. Pursue more immediate funding for Complete Streets multi-purpose trail replacement. FDOT complete two PHB's, enhanced RRFB project and mid-block crosswalk lighting project. | Pursue FDOT and MPO long-range funding for additional Complete Streets Design elements. | Continue pursuing long-term funding of GMD Complete Streets Corridor Plan projects in partnership with FDOT and MPO. See MPO Long Range Transportation Plan (“LRTP”) year 2030: Broadway Roundabout, Longboat Club Road Roundabout, full multi-purpose trail widening and replacement. Long-range funding for other complete streets elements.
Canal Dredging | Town staff hire consultant; consultant refine approach and funding scenarios for TC approval. Begin developing program approach. | Begin developing Finalize special assessment program approach and draft assessment resolutions. Meet with the public. | Finalize assessment resolutons and begin collecting assessments. Hire outside program /assessment manager to help organize inital program and collections. Prioritize first year area, and begin design and update permits as needed. | 1st Year Assessments complete; finalize design/permitting and begin first year of three-year Geographic Area Navigational Dredge program. | 2nd Year Assessments complete; design/permit then initiate dredge second year of three- year Geographic Area Navigational Dredge program. | 3rd Year Assessments complete; design/permit third year dredge and continue with maintenance dredging.
Town Center Phase 3 | Town Commission approved community center functions on south buildable parcel to include public library, adult life-long learning, and multi-purpose flex/performing arts space. Town pursue partner(s)/operator, as applicable. | Town work with Sarasota County on Library planning and funding for south parcel. Town determine how to handle funding for "upgrades," such as 3,000-sf multi-purpose flex space, adult learning classrooms, and upper deck space. Sarasota County function as facility operator. Include Rec Center fitness class space...(?). | Hold community charrettes and complete design of library with upgrades including Donor-funded design and permitting for community center on south parcel. Operator lead design with Town oversight. Ensure design re-evaluates parking availability. Town and County develop operator agreement and work on construction funding. and operating agreements. for development, programming and parking. | Pending Sarasota County, Town and donor funding, construct Phase 3 | Pending Sarasota County, Town and donor funding, construct Phase 3 | Evaluate options for the North Parcel.
|  | Sarasota County hire dedsign architect. Draft and finalize Preliminary Agreements with operator, as applicable. LBK Foundation begin donor effort. Subject to County for a library decision. | LBK Foundation begin continues donor efforts for construction elements as necessary.
Public Library Services on Island (related to Town Center Phase 3 above) | Continue discussions and formally ask for County to fund a new library on Longboat Key. Seek County support to fund design and construction in their CIP. | Work with Sarasota County to implement community input sessions and planning / design of new library. Continue discussions with Manatee County for services and location at Whitney Plaza. | Finalize design. Seek County construction dollars to advance project. Seek private funding for aspects of the facility. | Construction continued …. | Construction
Barrier Island Traffic Recommendations | Work with FDOT and adjacent communities on advancing major bridge replacement projects. Continue participation in BITS committee; support LBK and short-term adjacent community projects that add value to off island congestion reduction. | Coordinate with FDOT on evaluation of U.S. 41 @ Gulfstream Roundabout A effectiveness. Depending on effectiveness, advocate for John Ringling Counter-Flow and/or other solutions. | Continue to advocate for and pursue improvements to peak season congestion. Evaluate opportunities for water taxis/ferries to and from the island including potential landing sites. |  | Continue to advocate for and pursue improvements to peak season congestion. FDOT bridge planning/ design/ construction as applicable.
Smart City Opportunities Enhanced Communications Infrastructure | Implement with at least one carrier (preferably two or three) equipment distribution on island that enhances cell coverage on the island. | Once carrier coverage is improved, Town consider RFP process to solicit for partner/operator to implement Smart City infrastructure on the island. Pending costs and interest, Town can decide most practical, cost-effective, value-added Smart City solutions to island residents and visitors. OR, the Town plan gradual implementation and operation of its own suite of Smart City solutions. | If RFP is issued and operator selected, Town decide most practical, cost-effective, value-added Smart City solutions with operator expertise / input to provide enhanced Smart City services to island residents and visitors. | Execute Long-Term Contract/Agreement: 20-year in 5-year increments. OR, Town begin implementation of Smart City solutions, secured and potentially supported by a third party. | Technology adjustments based on current conditions.
Smart City Opportunities |  | Implement a pilot of Smart City solutions (iOT) that add value to the Town and enhance self-service to the community (FY23/24) | Evaluate current system and determine other possible options to add
Rec Center- Bayfront Park |  | Initiate concept planning for the ultimate replacement of the Rec Center - potentially with a 2-story open air structure that can provide storage, parking and other space underneath for the Town while still facilitating outdoor activities at the Park | If existing structure still in service- replace existing rec center roof FY 24. Town Center Phase 3 plan for fitness class space…(?) | Initiate concept planning for the ultimate replacement of the Rec Center - potentially with a 2-story open air structure that can provide storage, parking and other space underneath for the Town while still facilitating outdoor activities at the Park | Upon construction completion Town Center Phase 3, repurpose Bayfront Park rec center location. | Upon construction completion Town Center Phase 3, plan for future repurposing of Bayfront Park rec center location.
Evaluation of Commercial and Tourism balance |  |  | Start an analysis/study of issues including Commercial/Jobs/Tourism Housing Balance | Consider Comprehensive Plan/Town Code Updates/Revisions
Coordinated effort to advance resiliency initiatives within the Town | Internal pilot program of battery operated blower. | Evaluate battery operated blower pilot program once delivery received. Research grant programs specific to Public EV Charging Stations and current ordinances related to private installations on the island. Develop recommendations for a future Commission workshop. Evaluate vehicle replacement with EV vehicles. Pursue partnership with Sarasota Bay Estuary Program for an environmental project on the island. Perform an energy audit of Town facilities. | Continue the analysis/study of market, infrastructure and regulatory controls to ready the Town for potential opportunities/challenges in these areas. | Consider Comprehensive Plan/Town Code Updates/Revisions
Water System Augmentation and Reclaim Water on the Island |  | Explore modifications to City of Sarasota Interconnect agreement for high-usage seasons. Evaluate other engineering options to augment system. | Conduct feasibility study for island reclaim water to serve irrigation. Feasibility to include reclaim source, infrastructure requirements, and planning level costs.
Gulf of Mexico Drive Lighting: New Lit Street Name Signs, additional roadway lighting, and Mutlit-Use Trail Lighting |  | Review options and costs for new lit street name signs Town wide. Select an option to implement in FY 2024. | Implement new lit street name signs. In addition, assess GMD lighting after Underground Project is complete and lit street name signs installed. Develop options for additonal roadway and pathway lighting. Work with Town Manager and Town Commisison.